## Sheet1
Team Knuth Change Log | Version 1 - Created 22/03/19
Ryan Pickering |  |  | Matthew Randle |  |  | Matthew Ritchard |  |  | Ethan Roe
Change | Made By | Date | Change | Made By | Date | Change | Made By | Date | Change | Made By | Date
Created Draft Project Proposal |  |  | Completed skills audit |  |  | Completed skills audit |  |  | Completed skills audit
Created team meeting minutes template |  | 2019-02-07
Created Gantt Chart v1
Completed skills audit
Completed project proposal
Completed first team meeting minutes
Created Draft Risk Analysis
Created Draft Quality Manual
Created Draft Progress Report
Created Draft Code of Conduct
Created Draft Task Prioritisation |  | 2019-02-10
Created Meeting 2 Minutes |  | 2019-02-15
Added further risks to risk assessment
Added risk value to risk assessment
Split risk assessment management to avoidance strategy and mitigation
Updated progress report
Inputted mitigation techniques
Created new meeting minutes
completed risk assessment
Created Gantt Chart v2
Drew Job Card Template
Created job Card template using scene builder
Added CSS to completed button
Added save functionality to save jobcard to database
added update functionality to overwrite current values in database
Added ability to load tasks to the job card
Reformatted the GUI
Updated progress report
Added suspended checkbox
Added navigation menu
Created confirmation messages for when a user does an action
Added sort tasks by task urgency
Created new Gantt chart
Created new meeting minutes
Updated Gantt chart
Added new fields to Task table in the database
Updated task prioritisation
Updated progress report
Created new meeting minutes
Transferred buttons to navigation menu on job card
Created new gantt chart
Added export job card to text document