## Sheet1
Team Knuth Change Log
Ryan Pickering |  | Matthew Randle |  | Matthew Ritchard |  | Ethan Roe
Change | Date | Change | Date | Change | Date | Change | Date
Created Draft Project Proposal |  | Completed skills audit |  | Completed skills audit | 2019-02-18 | Completed skills audit | 2019-02-18
Created team meeting minutes template | 2019-02-07 | Created user accounts in database |  | created class Diagram V1 | 2019-03-01 | Created statement of the purpose of the system | 2019-02-18
Created Gantt Chart v1 |  | Added login component |  | created sequence Diagramv1 | 2019-03-02 | Created use case diagram v1 | 2019-02-18
Completed skills audit |  | Created scene controller for navigation |  | created class Diagram V2 | 2019-03-04 | Created use case desciptions v1 | 2019-02-18
Completed project proposal |  | Created user account page |  | created class Diagram v3 | 2019-03-09 | Created template for mission | 2019-03-04
Completed first team meeting minutes |  | Made it so only relevant data will show to user |  | created Task.java | 2019-03-20 | Added functionality to suspend a job | 2019-03-18
Created Draft Risk Analysis |  | Added jobs, parts, users and tasks tables to user account page |  | created taskController.java | 2019-03-28 | applied functionality to buttons/ choicebox's | 2019-03-18
Created Draft Quality Manual |  | If username or password doesn’t exist, a error is shown |  | created TaskAllocate.fxml | 2019-03-28 | Added functionality to suspend a task | 2019-03-23
Created Draft Progress Report |  |  |  | added table view to task controller | 2019-04-04 | Added functionality to check If task is completed | 2019-03-23
Created Draft Code of Conduct |  |  |  | added buttons to sort table | 2019-04-05 | updated use case diagram v2 | 2019-03-25
Created Draft Task Prioritisation | 2019-02-10 |  |  | added search username option | 2019-04-07 | updated use case desciptions v2 | 2019-03-25
Created Meeting 2 Minutes | 2019-02-15 |  |  | added button to assign username and urgency to task | 2019-04-10 | applied functionality to buttons for suspend/ complete tasks | 2019-03-28
Added further risks to risk assessment |  |  |  | added functionality to automatically work out due/assign date | 2019-05-01 | created functionality to alert management of an overdue task | 2019-04-15
Added risk value to risk assessment |  |  |  | changed usernames from textfields to drop down | 2019-05-02 | created functionality to alert customer services of overdue job | 2019-04-26
Split risk assessment management to avoidance strategy and mitigation |  |  |  | added overdue filter | 2019-05-05 | completed functionality for each part of mission | 2019-05-06
Updated progress report |  |  |  | added error handling if statements | 2019-05-06 | updated use case diagram v3 (final) | 2019-05-07
Inputted mitigation techniques |  |  |  | created class diagram v4 | 2019-05-06 | updated use case desciptions v3 (final) | 2019-05-07
Created new meeting minutes |  |  |  | created sequenceDiagram v2 | 2019-05-07
completed risk assessment |  |  |  | created stateDiagam v1 | 2019-05-07
Created Gantt Chart v2 |  |  |  | made a textfield to view the due date and assigned date on selected task | 2019-05-08
Drew Job Card Template
Created job Card template using scene builder
Added CSS to completed button
Added save functionality to save jobcard to database
added update functionality to overwrite current values in database
Added ability to load tasks to the job card
Reformatted the GUI
Updated progress report
Added suspended checkbox
Added navigation menu
Created confirmation messages for when a user does an action
Added sort tasks by task urgency
Created new Gantt chart
Created new meeting minutes
Updated Gantt chart
Added new fields to Task table in the database
Updated task prioritisation
Updated progress report
Created new meeting minutes
Transferred buttons to navigation menu on job card
Created new gantt chart
Added export job card to text document