## Sheet1
[8 empty] | Reporting Period |  | 04/03/19 - 03/04/19
|  |  |  | Key: | Pickering | Pritchard | Randle | Roe | Group | [8 empty] | DEADLINE
|  |  |  | Febuary | Febuary | Febuary | Febuary | March | March | March | March | April | April | April | April | April | May | May
|  |  |  | Sprint 1 | Sprint 1 | Sprint 1 | Sprint 2 | Sprint 2 | Sprint 2 | Sprint 3 | Sprint 3 | Sprint 3 | Sprint 4 | Sprint 4 | Sprint 4 | Sprint 4 | Sprint 5 | Sprint 5
|  |  |  | 4th - 10th | 11-17th | 18-24th | 25th-3rd | 4th-10th | 11th-17th | 18th-24th | 25th-31st | 1st-7th | 8-14th | 15th-21st | 22nd-28th | 29th-5th | 6th-12th | 13th-19th
Task | Priority | Start | Done | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15
Initial Planning Meeting
Skills Audit | 1 | 1 | 3
Project Proposal | 1 | 2 | 3
Code of Conduct | 2 | 2 | 3
Risk Analysis | 1 | 2 | 8
Quality Manual | 2 | 2 | 8
Progress Report | 2 | 2 | 14
Change Log | 2 | 1 | 14
System Purpose Statement | 2 | 2 | 5
UML Use Case Diagram | 1 | 2 | 8
Use Case Descriptions | 1 | 2 | 6
Class Diagram | 1 | 2 | 6
State Machine Diagrams | 2 | 2 | 6
Sequence Diagrams | 2 | 2 | 6 | [5 empty] | ◆
Create Database | 1 | 2 | 5 |  |  |  |  | ◆
Design GUI | 3 | 2 | 2
Create Initial GUI | 3 | 3 | 3
Job Progress Component | 1 | 5 | 9
Task Allocation Component | 1 | 5 | 9
User Account Component | 1 | 5 | 9
Job Delay Component | 1 | 5 | 9 | [8 empty] | ◆
Statistics Component | 1 | 9 | 12
Testing | 1 | 12 | 13 | [12 empty] | ◆
Scrum | 1 | 3 | 13
Sprint Review | 1 | 3 | 13
Submission | 1 | 14 | 14 | [13 empty] | ◆